## Northeast
Northeast
Project name | Pipeline | Capacity (Bcf/d) | Affected Route | Status | Project Details
Rockaway Delivery Lateral and Northeast Connector | Williams' Transcontinental Gas Pipeline (Transco) | 0.63122 | Marcellus/Utica Region to New York City | Construction on both facilities commenced on June 9, 2014, with a targeted in-service date of November 1, 2014. | Compressor station modificantions and expansions (Northeast Connector) and construction of new lateral pipeline (Rockaway Delivery Lateral).
Line MB Expansion | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.12 | Marcellus/Utica region to Maryland | In-service authorization requested for Phase 1 by October 24, 2014. Originally planned for completion of October 2013 (phase 1) and October 2014 (phase 2), prior to project delays. | Construction of new pipeline to extend Columbia's Line MB.
Line 1570 Project | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.096585 | Marcellus/Utica Region in Pennsylvania | In-service authorization requested for October 24, 2014. | Line replacements and compressor station modifications to increase capacity to an interconnect with Tetco in Pennsylvania.
Rose Lake Expansion Project | Kinder Morgan's Tennessee Gas Pipeline | 0.22439 | Marcellus/Utica Region in Pennsylvania | Partially in-service, with full in-service authorization requested for November 1, 2014. | Modifications and expansions to three compressor stations on the TGP 300 line in Pennsylvania.
TEAM 2014 | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.58537 | Marcellus/Utica Region to New York, Ohio, and Louisiana | In-service authorization requested for October 24, 2014. | Looping pipelines and compressor station expansions and upgrades in Pennsylvania.
Wright Interconnect Project | Iroquois Pipeline | 0.63 (all of which is received off of Constitution) | Marcellus/Utica to New York and New England | Filed. Targeted in-service for March 2015. | Expansions and modifications to the Wright compressor station to allow gas delivered from the Constitution Pipeline to flow to New York and New England on Iroquois and TGP.
East Side Expansion | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.30439 | Marcellus/Utica region to New York | Filed. Targeted in-service for September 2015. | Modified compressor stations and looping lines in Pennsylvania and New Jersey; modified metering station in New York, and a compressor station modification in Maryland.
Niagara Expansion Project | Kinder Morgan's Tennessee Gas Pipeline | 0.14634 | Marcellus/Utica Region to New York | Filed. Targeted in-services for November 2015. | Looping pipeline and compressor station expansions in New York State.
Northern Access 2015 | National Fuel Gas Supply pipeline | 0.13659 | Marcellus/Utica to U.S.-Canada border | Filed. Targeted in-service for November 2015. | Two new compressor stations and modifications to a metering station in western New York, to flow gas north from an interconnect with TGP in northern Pennsylvania, to a separate interconnect with TGP in upstate New York. National Fuel will lease the additional capacity to TGP, to flow gas to their U.S.-Canadian border crossing.
West Side Expansion and Modernization Project | National Fuel Gas Supply pipeline | 0.17073 | Marcellus/Utica to U.S.-Canada border | Filed. Targeted in-service for November 2015. | A new pipeline, new compressor station, and modifications to existing compressor stations on an existing route to move additional gas out of western Pennsylvania.
Constitution Pipeline | Williams and Cabot Oil & Gas | 0.63415 | Marcellus/Utica Region to New York | Filed. Targeted in-service for late 2015 or 2016. | New pipeline from Pennsylvania to New York.
Northern Access 2016 | National Fuel's Emprie Pipeline | 0.34146 | Marcellus/Utica to U.S.-Canada border | Pre-filing. Targeted in-service for November 2016. | New pipeline and compressor station from northern Pennsylvania to an interconnect with TGP and the Supply Transmission Pipeline in Erie, New York, plus additional facilities to move gas from Supply pipeline to the existing Empire pipeline in Niagara, New York.
Algonquin Incremental Market Project | Spectra's Algonquin Gas Transmission (AGT) pipeline | 0.33366 | Marcellus/Utica to New England | Filed. Targeted in-service for November 2016. | New looping pipelines and modifications on six compressor stations on AGT.
New Market Project | Dominion Transmission (DTI ) pipeline | 0.10927 | Marcellus/Utica to New York Markets | Filed. Targeted in-service for November 2016. | Two new compressor stations, and expansions to existing compressor stations, to increase gas deliveries to upstate New York and New York City.
South-to-North Project | Iroquois Pipeline | up to 0.29 | Marcellus/Utica to the U.S.-Canada border | Announced. Targeted in-service for November 2016. | Expansions to reverse flows on existing pipeline to take gas from interconnects with DTI, Consitution, and Algonquin pipelines to interconnect with TransCanada.
Nexus Gas Transmission Project | DTE Energy and Spectra Energy | up to 2.00 | Marcellus/Utica region to Ontario, Canada | Announced. Targeted in-service of fourth quarter 2017, supplemental open season ended in August. | New pipeline and compressor stations from an interconnect with TGP in eastern Ohio to DTE pipeline near Detroit, and the Dawn Hub in Ontario.
Atlantic Bridge Project | Spectra's Algonquin Gas Transmission (AGT) and Maritimes and Northeast (M&N) pipelines | 0.098 to 0.585 | Marcellus/Utica to U.S.-Canada border | Announced. Targeted in-service for November 2017. | Expansions on existing right-of-way from Ramapo, New York to the border between Maine and Canada.
PennEast Pipeline | AGL Resources, NJR Pipeline Company, Public Service Enterprise Group, South Jersey Industries, and UGI Energy Services | up to 1.00 | Marcellus/Utica to New Jersey | Announced. Targeted in-service for late 2017. | New pipeline and compressor stations connecting two points on the Transco Pipeline, running from northeastern Pennsylvania to central New Jersey.
Diamond East Project | Williams' Transcontinental Gas Pipeline (Transco) | 1 | Marcellus/Utica Region to New York | Announced. Targeted in-service for mid-2018. | New parallel (looping) pipelines and compressor station modifications in Pennsylvania and New Jersey.
Northeast Energy Direct Project | Kinder Morgan's Tennessee Gas Pipeline | up to 2.20 | Marcellus/Utica Region to New England | Pre-filed on September 17, 2014, with targeted in-service for November 2018. | New pipeline to New England.
Appalachia to Market Project | Spectra's Texas Eastern Transmission (Tetco) pipeline | up to 1.00 | Marcellus/Utica region to New Jersey | Announced. Targeted in-service as early as November 2018, open season ended at the end of August. | Expansions to eastbound flows from the M2 to the M3 portions of the Tetco mainline.
WB Xpress | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.90 to 2.00 | Marcellus/Utica region to Maryland, Virginia, and West Virginia | Pre-filing. Targeted in-service for second half of 2018, with some capacity as early as 2016. | Pipeline expansions to take 0.50 to 1.20 Bcf/d east to Virginia and the Cove Point LNG terminal, and 0.40 west to 0.80 Bcf/d to a TGP interconnect in West Virginia.
Access Northeast Project | Spectra's Algonquin Gas Transmission (AGT) and Maritimes and Northeast (M&N) pipelines | possibly more than 1.00, to be identified in 0.20 increments | Marcellus/Utica to New England | Announced. Targeted in-service for November 2018. | Expansions on AGT and M&N in increase gas delivery to northeastern power plants.
QuickLink Project | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.4878 | Marcellus/Utica region - Ohio to West Virginia and Pennsylvania | No new developments since 2012 open season. Originally targeted in-service for November 2015. | Expansions from Ohio processing plants to interconnects with multiple other pipelines (DTI, Tetco, REX).

## Midwest
Midwest
Project name | Pipeline | Capacity (Bcf/d) | Affected Route | Status | Project Details
Rose Lake Expansion Project | Kinder Morgan's Tennessee Gas Pipeline | 0.22439 | Marcellus/Utica Region in Pennsylvania | Partially in-service, with full in-service authorization requested for November 1, 2014. | Modifications and expansions to three compressor stations on the TGP 300 line in Pennsylvania.
Southeast Main Line (SEML) expansions | TransCanada's ANR Pipeline | 2 | western Ohio to Gulf and Midwest | Various stages of development, with 1.25 Bcf/d expected by the end of 2014, and the remaining 0.75 Bcf/d in 2015. | Expansions to compressor and metering stations completed in phases to move an additional 2.00 Bcf/d both north and south on the SEML, with at least 0.60 Bcf/d going to the Gulf Coast.
Zone 3 East-to-West Project | Tallgrass' Rockies Express Pipeline | 1.1707 | Marcellus/Utica region to Illinois | Filed. Targeted in-service for mid-2015. | Compressor station modifications and expansions to allow westbound flows from Ohio to an interconnect with NGPL.
Utica Backhaul | Kinder Morgan's Tennessee Gas Pipeline | 0.4878 | Marcellus/Utica Region to Gulf Coast | Announced. Targeted in-service for November 2015. | Modificantions at three compressor stations in West Virginia.
Uniontown to Gas City Expansion Project | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.41463 | Marcellus/Utica region to Indiana | Filed. Targeted in-service for fourth quarter 2015. | Compressor station modification to allow westbound flows of gas to an interconnect with the Panhandle Eastern Pipe Line.
Clarington Project | Dominion Transmission (DTI ) pipeline | 0.2439 | Marcellus/Utica to Ohio interconnects | Filed. Targeted in-service for November 2016. | Compressor station expansions in West Virginia and Ohio to allow westbound flows on DTI to interconnects with Tetco, which will be able to flow this gas south, REX, which will be able to flow it west.
Clarington West Project | Tallgrass' Rockies Express Pipeline | up to 2.40 | Marcellus/Utica region to Illinois | Announced. In-service targeted for between the second quarter of 2016, and the second quarter of 2017. | Possibly looping lines and/or expansions/modifications to existing compressor stations
ET Rover | Energy Transfer (ET) | 3.25 | Marcellus/Utica to Ohio, Michigan, and Canada | Announced. Service to Midwest Hub targeted for December 2016, service to Dawn targeted for June 2017 | New pipeline and compressor stations to move gas from Cadiz, Ohio, to an interconnect in Definace, Ohio (ANR), two interconnects in Michigan, and the Dawn Hub in Canada.
ANR East Pipeline Project | TransCanada's ANR Pipeline | 1.20 to 2.00 | Marcellus/Utica to Indiana, Illinois, and Michigan | Announced. Targeted in-service for third quarter of 2017. | New pipeline and compressor facilities to deliver gas west from Ohio to interconnects with the Gulf mainline, Great Lakes Gas Transmission (GLGT) pipeline, and/or possibly DTI, Tetco, and EQT.
Mountaineer Xpress | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.73 to 2.44 | Marcellus/Utica region southwest through West Virginia | Announced. Service targeted for the fourth quarter of 2018, with initial capacity possible as early as 2017. | Expansions to bring natural gas production from Ohio, West Virginia, and Pennsylvania through West Virginia.

## Southeast
Southeast
Project name | Pipeline | Capacity (Bcf/d) | Affected route | Status | Project details
Gulf Bi-Direction Project | NiSource's Columbia Gulf Transmission (CGT) pipeline | 0.53 | Kentucky to Louisiana - Marcellus/Utica gas to come from Smithfield III below | In service. | Compressor station modifications, expansions, and addition in West Virginia and Pennsylvania to transport gas to existing expansions extending to Louisiana.
TEAM - South Expansion Project | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.29268 | Marcellus/Utica Region to Mississippi | Targeted in-service for November 2014, with initial service reportedly beginning in September. | Expansions to existing compressor stations.
TEAM 2014 | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.58537 | Marcellus/Utica Region to New York, Ohio, and Louisiana | In-service authorization requested for October 24, 2014. | Looping pipelines and compressor station expansions and upgrades in Pennsylvania.
Smithfield III Expansion Project | NiSource's Columbia Gas Transmission (TCO) pipeline | 0.43317 | Marcellus/Utica region southwest to Kentucky | In-service requests approved for two compressor stations. Full in-service targeted for November 2014. | Compressor station modifications, expansions, and addition in West Virginia and Pennsylvania to transport gas to Gulf Bi-Direction facilities.
Ohio Pipeline Energy Network (OPEN) | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.53659 | Marcellus/Utica region to Louisiana | Filed. Targeted in-service for fourth quarter 2015. | New pipeline and compressor station in Ohio, compressor station modifications in Ohio, Kentucky, Mississippi, and Louisiana.
Utica Backhaul | Kinder Morgan's Tennessee Gas Pipeline | 0.4878 | Marcellus/Utica Region to Gulf Coast | Announced. Targeted in-service for November 2015. | Modificantions at three compressor stations in West Virginia.
Broad Run Flexibility Project | Kinder Morgan's Tennessee Gas Pipeline | 0.57561 | Marcellus/Utica Region to Tennessee and Kentucky | Announced. Targeted in-service for November 2015. | Compressor station expansions and modifications in West Virginia, Kentucky, and Tennessee.
Leidy Southeast | Williams' Transcontinental Gas Pipeline (Transco) | 0.5122 | Marcellus/Utica Region to Alabama | Filed. Targeted in-service date of December, 2015. | New parallel (looping) pipelines and compressor station modifications in Pennsylvania and New Jersey.
Ohio to Louisiana Access Project | Boardwalk's Texas Gas Transmission (TGT) pipeline | 0.626 | Marcellus/Utica to Louisiana | Filed. Targeted in-service for June 2016. | Modificantions and new facilities to provide backhaul capacity from interconnect with REX in Lebanon, OH, to the Gulf South Pipeline down to Zone SL in Louisiana.
Gulf Coast mainline expansion | Kinder Morgan's Natural Gas Pipeline (NGPL) | 0.73171 | Marcellus/Utica region to Louisiana and Texas | Announced. In-service targeted for July 2016. | Expansions from NGPL's interconnect with REX in Illinois to the Henry Hub in Louisiana, additional Gulf Coast facilities in Texas
Northern Supply Access Project | Boardwalk's Texas Gas Transmission (TGT) pipeline | 0.18 | Marcellus/Utica to Louisiana | Announced. Targeted in-service for April 2017. | New compressor station, existing compressor expansions, pipeline modifications, and new interconnects.
Dalton Expansion Project | Williams' Transcontinental Gas Pipeline (Transco) | 0.43707 | Marcellus/Utica Region to Georgia and Mississippi | Pre-filed. Targeted in-service for May 2017. | New lateral pipelines and compressor stations in Georgia, and modifications to compressor stations in Virginia.
Atlantic Sunrise | Williams' Transcontinental Gas Pipeline (Transco) | 1.6585 | Marcellus/Utica Region to Alabama | Pre-filed. Targeted in-service for second half of 2017. | New pipeline and compressor stations in Pennsylvania.
Leach Xpress | NiSource's Columbia Gas Transmission (TCO) pipeline | 1.5 | Marcellus/Utica region to Kentucky | Pre-filing approved. Targeted in-service for second half of 2017. | Expansions on the CGT mainline to its interconnect with Colombia Gulf Transmission.
Rayne Xpress | NiSource's Columbia Gas Transmission (TCO) pipeline | 1 | Marcellus/Utica region to Kentucky | Announced. Targeted in-service for second half of 2017. | Additional compression on the CGT mainline to its interconnect with Colombia Gulf Transmission.
Broad Run Expansion Project | Kinder Morgan's Tennessee Gas Pipeline | 0.19512 | Marcellus/Utica Region to Tennessee and Kentucky | Announced. Targeted in-service for November 2017. | Compressor station expansions and modifications in West Virginia, Kentucky, and Tennessee.
Gulf Markets Expansion | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.63415 | Marcellus/Utica region to Louisiana, South Texas to Louisiana | Pre-filing. Targeted in-service for Phase 1 in November 2016 (.24 Bcf/d), Phase 2 (.39 Bcf/d) in November 2017. | New compressor stations in Ohio, South Texas, and Louisiana to move gas south to the Cameron LNG facility.
Access South Project | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.3122 | Marcellus/Utica region to Mississippi | Announced. Targeted in-service for November 2017, open season ended at the end of August. | Expansions to southbound flows from the M2 to the M1 portions of the Tetco mainline.
Adair Southwest Project | Spectra's Texas Eastern Transmission (Tetco) pipeline | 0.19512 | Marcellus/Utica region to Kentucky | Announced. Targeted in-service for November 2017, open season ended at the end of August. | Expansions to southbound flows from the M2 to the M1 portions of the Tetco mainline.
Western Marcellus Pipeline Project | Williams' Transcontinental Gas Pipeline (Transco) | 1.00 to over 2.00 | Marcellus/Utica Region to Mid-Atlantic and Southeast | Announced. Targeted in-service for fourth quarter of 2018. | New pipeline from REX interconnect in Ohio and a separate interconnect in West Virginia to the Transco mainline in southern Virginia.
Mountain Valley Pipeline | Equitrans (EQT) and NextEra Energy | 1.9512 | Marcellus/Utica to southern Virginia | Announced. Targeted in-service for fourth quarter of 2018. | New pipeline and compression facilities from Equitrans' Mobley processing plant in West Virginia to an interconnect with the Transco Pipeline in southern Virginia.
Atlantic Coast Pipeline | Dominion Transmission (DTI ) pipeline, with Piedmont Natural Gas, Duke Energy, and AGL Resources. | 1.5 | Marcellus/Utica to North Carolina | Announced. Targeted in-service for late 2018. | New pipeline plus three compressor stations from West Virginia to North Carolina.
Spectra Energy Pipeline Project | Spectra Energy | 1.00 or more | Marcellus/Utica region to North Carolina | On-hold. Targeted in-service for fourth quarter of 2018. | New pipeline from Pennsylvania to North Carolina.